## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Online Bio-Informatics Toolkit | [6 empty] | Completed | 1
| Team Members: | Paul Ryu, Ansleigh Yancey, Ben Williams, Mason Monday, Sadaira Packer | [6 empty] | Discarded | 2
| Date: | 2019-02-10 | Cycle: | 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To develop an interactive, online database that is searchable by disease type or tissue and cell lines. Users will also be able to request to add an entry into the database. | [6 empty] | In Review
Unstarted
| Cycle Intent: | To add functionality to search through a subset of our database based on cell line and/or disease type
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Add Entry Request(Text Box) |  | 2 | 30 | 0 | Collaboration | 2.5 | 2.5
2 | Add Entry Request(Text File) |  | 2 | 30 | 0 | Unstarted | 0 | 0
3 | Add Entry via Text Box(Administrator) |  | 2 | 20 | 5 | Unstarted | 0 | 0
4 | Add Entry via File(Administrator) |  | 2 | 20 | 0 | Unstarted | 0 | 0
5 | Delete Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
6 | Delete Entry(Administrator) |  | 2 | 20 | 0 | Unstarted | 0 | 0
7 | Edit Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
8 | Edit Entry(Administrator) |  | 2 | 25 | 0 | Unstarted | 0 | 0
9 | Search for Database Entry (Cell Line) |  | 1 | 40 | 40 | Collaboration | 31 | 31
10 | Search for Database Entry (Disease Type) |  | 1 | 40 | 40 | Collaboration | 31 | 31
11 | Search for Database Entry (Cell Line & Disease Type) |  | 1 | 40 | 40 | Collaboration | 31 | 31
12 | Download Search Results |  | 2 | 25 | 3 | Collaboration | 2 | 2
|  |  | Planned Total | 350 | 128 | Actual Total | 97.5 | 97.5

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Design Team 9
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Mason Monday | 9,10,11 |  |  | 9,10,11 | 40 | 0 | 0 | 6 | 6 | 1 | 1 | 0 | 0 | 7 | 7
| Ansleigh Yancey | 1,12 | 1,12 | 1,12 |  | 50 | 1 | 1 | 2 | 2 | 1 | 1 | 8 | 8 | 12 | 12
| Paul Ryu | 9,10,11 | 11 | N/A | 9,10,11 | 30 | 0 | 0 | 8 | 8 | 0 | 0 | 1 | 1 | 9 | 9
| Sadaira Packer | 9,10,11 |  |  | 9,10,11 | 40 | 0 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 8 | 8
| Ben Williams | 9,10,11 | 11 | N/A | 9,10,11 | 30 | 0 | 0 | 2 | 2 | 1 | 1 | 4 | 4 | 7 | 7
[5 empty] | Totals | 190 | 1 | 1 | 26 | 26 | 3 | 3 | 13 | 13 | 43 | 43
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| In the first week of this cycle, we have gained a better understanding of our application's search objectives and functionality. We have improved the user interface and made it more visually appealing. We have also created a system for entry submissions, that may be subject to change. Additionally, we implemented the download functionality for search results. | [6 empty] | The client has explained which portions of the datasets are necessary to the project and which are not. Thus, our objective is to develop a clean and efficient way to merge the datasets, either by using an existing library/function or creating a completely new algorithm that we can tailor to our client and project.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| The client has specified which portions of the datasets are vital to the project so that we can merge the data into a database cleanly but it is still unclear on how to do the key part of the project, which is to analyze the datasets and see which components are enriched when compared to each other. It will most likely have to be a more mathematical solution like other Genome Signal Processing methods and thinking of a way that our group can achieve this without more help from the client is slightly daunting. Group members also have scheduling conflicts and it is difficult to get all five members together at once. | [6 empty] | We have learned many things thus far from the project but there is still a lot of work to do.
Risks facing the project:
The further we do not clarify with the client on what exactly we need to do with the data, the further the chances are that we deviate from the project's end goal. To eliminate the risks, we need to completely clarify what types of algorithms are needed and how complex the data manipulation processes need to be.

## Mason Monday Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Mason Monday
Week Ending: |  | 2019-02-10
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2019-02-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Dr. Chen Meeting
Date: | 2019-02-07 | Result: | Better understanding of needs for searching through database
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Friday | Task(s) performed:
Date: | 2019-02-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Documentation of dataset, research on topic, search algorithm brainstorming
Date: | 2019-02-09 | Result: | More complete understanding of search requirements, pseudocode prototype of search algorithm
Hours Worked: | 4 | Problems encountered: | Lack of cumulative information on dataset's properties online
Day: | Sunday | Task(s) performed: | Research into given datasets
Date: | 2019-02-10 | Result: | Better understanding of data qualities
Hours Worked: | 2 | Problems encountered: | Very jumbled information

## Benjamin Williams Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Bio-informatics Toolkit
Member: |  | Benjamin Williams
Week Ending: |  | 2019-02-10
Cycle: |  | Cycle 1
Team Member Work Summary
Day | Monday | Task(s) performed:
Date: | 2019-02-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Met with Dr. Chen to further clarify project requirements.
Date: | 2019-02-07 | Result: | Further understanding of how to intersect two datasets based on chromosome type and position
Hours Worked: | 1 | Problems encountered: | N/A
Day: | Friday | Task(s) performed:
Date: | 2019-02-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Met with group to fill out status report and discuss meeting with Dr. Chen. Searched the datasets for similarities.
Date: | 2019-02-09 | Result: | Status report mostly completed, team has better understanding of the project.
Hours Worked: | 2 | Problems encountered: | Paul was out of town
Day: | Sunday | Task(s) performed: | Remove irrelevant information (Score, Name) when using the .bed dataset. Filter .TAB dataset for trait, chromosome, and position. Find any intersections between the two datasets
Date: | 2019-02-10 | Result: | N/A
Hours Worked: | 4 | Problems encountered: | Working past 3:00 when status report is due.

## Ansleigh Yancey Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Bio-Informatics Toolkit
Member: |  | Ansleigh Yancey
Week Ending: |  | 2019-02-10
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2019-02-04 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Worked on UI to make more visually appealing
Date: | 2019-02-05 | Result: | Created a more interesting layout
Hours Worked: | 2 | Problems encountered: | Had to figure out how to create a dashboard instead of a navigation page in Shiny
Day: | Wednesday | Task(s) performed: | Worked on UI color scheme
Date: | 2019-02-06 | Result: | The webpage has a more appealing color story
Hours Worked: | 1.5 | Problems encountered: | None
Day: | Thursday | Task(s) performed: | Worked on integrating the text box feature for data entry submissions
Date: | 2019-02-07 | Result: | A user can enter data into a text box and it will send it to an email address when clicking send
Hours Worked: | 2.5 | Problems encountered: | No real issues. Learning to do this in Shiny was difficult but doable
Day: | Friday | Task(s) performed:
Date: | 2019-02-08 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed: | Worked on fixing the download option on the search tab
Date: | 2019-02-09 | Result: | Can name a file and save it to the computer, though search functionality is still not complete
Hours Worked: | 2 | Problems encountered: | There was already a UI in place for this but did not function properly
Day: | Sunday | Task(s) performed: | Worked on the status report time logs
Date: | 2019-02-10 | Result: | Finished the assignment
Hours Worked: | 1 | Problems encountered:

## Sadaira Packer Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Bio-Informatics toolkit
Member: |  | Sadaira Packer
Week Ending: |  | 2019-02-10
Cycle: |  | CYCLE 1
Team Member Work Summary
Day | Thursday | Task(s) performed: | Worked on figuring out how to connect two dataframes in R
Date: | 2019-02-07 | Result: | There is a merge function in R that can be used to merge two dataframes with a common column. Unsure if we can apply this or if we need to find another way.
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed: | Worked on understanding the meaning of each column of the first dataset
Date: | 2019-02-08 | Result: | We only need to focus on the "chromosome start" and "chromosome end" columns
Hours Worked: | 2 | Problems encountered:
Day: | Saturday | Task(s) performed: | Worked on figuring out what each column of the disease database means and how to relate it to the other database
Date: | 2019-02-09 | Result: | Ruled out a few columns that I'm sure won't be a factor, such as the PubMed column and the source column. I also don't think the p-values would be useful in relating the two.
Hours Worked: | 1.5 | Problems encountered:
Day: | Sunday | Task(s) performed: | Continued looking into how to relate the two dataframes
Date: | 2019-02-10 | Result: | I belive that either the SNP, position, or gene region values of the disease database will help us relate the two databases. I need to further look into these terms to obtain a better understanding of them.
Hours Worked: | 2.5 | Problems encountered: | Trying to find information leads to more confusing terms which leads to searching for definitions of definitions.
Day: |  | Task(s) performed:
Date: |  | Result:
Hours Worked: |  | Problems encountered:

## Paul Ryu Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Paul Ryu
Week Ending: |  | 2019-02-10
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed: | N/A
Date: | 2019-02-04 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Tuesday | Task(s) performed: | Researched what it means to do genomic signal processing and how scientists and engineers previously carried out DNA sequence clustering to merge data
Date: | 2019-02-05 | Result: | I have more understanding on how to merge the datasets given to us by the client.
Hours Worked: | 4 | Problems encountered: | Studies are already debatably outdated and many of the algorithms used to merge the data are confusing, such as Voss, K-th Ordering, and using atomic numbers to measure nucleotide precision and accuracy.
Day: | Wednesday | Task(s) performed: | Contacted the client so that the group could meet and get more information about the datasets because we are still confused as to which pieces of data are supposed to interact with each other.
Date: | 2019-02-06 | Result: | The group is scheduled to meet the client and discuss the issues on Thursday, February 7 2019.
Hours Worked: | 0 | Problems encountered: | Scheduling conflict: The client could only meet when I had class and I will not be able to make the scheduled appointment.
Day: | Thursday | Task(s) performed: | N/A
Date: | 2019-02-07 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Friday | Task(s) performed: | Nothing on my part. Mason and Ben relayed the information from the client to me.
Date: | 2019-02-08 | Result: | Received information from Mason on how the meeting went and how the client described what needs to be done with the datasets. Researched more at home about data clustering methods for human genomes.
Hours Worked: | 4 | Problems encountered: | It is still difficult to understand exactly how the client wants the datasets to be merged. Specifications say that the outcome of the project is to note which pieces of genome signals seem "enriched" when compared to protein (expression) mutations but it could mean anything from an intermediate-level algorithm to an extremely complex and industry level process, especially when using a language like R that has limited libraries compared to others like Python with numpy, Vectorz for Java, etc. Current ways to do what the client asked consist of methods like predictive coding, dividing / fractal dimension vectors, and ordering the genomic signals into microarrays but these seem very out of scope to the project and impossible to learn as an undergraduate student. Need more involvement from the client in the perspective of back-end programming as it will be by far the most difficult portion of the project.
Day: | Saturday | Task(s) performed: | Group planned to meet physically at 1800 in the Shelby Senior Design Lab to work on the status report and discuss any issues about the project in general.
Date: | 2019-02-09 | Result: | Groupmates accomplished many things.
Hours Worked: | 0 | Problems encountered: | Could not come back into town from Birmingham on time to meet the group at 1800 because of an interview and unplanned tailoring issues at the suit company.
Day: | Sunday | Task(s) performed: | Filled out Status Report.
Date: | 2019-02-10 | Result: | Status Report
Hours Worked: | 1 | Problems encountered: | N/A