## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Online Bio-Informatics Toolkit | [6 empty] | Completed | 1
| Team Members: | Paul Ryu, Ansleigh Yancey, Ben Williams, Mason Monday, Sadaira Packer | [6 empty] | Discarded | 2
| Date: | 2019-02-21 | Cycle: | 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To develop an interactive, online database that is searchable by disease type or tissue and cell lines. Users will also be able to request to add an entry into the database. | [6 empty] | In Review
Unstarted
| Cycle Intent: | To add functionality to search through a subset of our database based on cell line and/or disease type
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Add Entry Request(Text Box) |  | 2 | 30 | 0 | Collaboration | 6.5 | 6.5
2 | Add Entry Request(Text File) |  | 2 | 30 | 0 | Unstarted | 4 | 4
3 | Add Entry via Text Box(Administrator) |  | 2 | 20 | 5 | Unstarted | 0 | 0
4 | Add Entry via File(Administrator) |  | 2 | 20 | 0 | Unstarted | 0 | 0
5 | Delete Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
6 | Delete Entry(Administrator) |  | 2 | 20 | 0 | Unstarted | 0 | 0
7 | Edit Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
8 | Edit Entry(Administrator) |  | 2 | 25 | 0 | Unstarted | 0 | 0
9 | Search for Database Entry (Cell Line) |  | 1 | 40 | 20 | Collaboration | 31 | 65
10 | Search for Database Entry (Disease Type) |  | 1 | 40 | 20 | Collaboration | 31 | 65
11 | Search for Database Entry (Cell Line & Disease Type) |  | 1 | 40 | 40 | Collaboration | 31 | 65
12 | Download Search Results |  | 2 | 40 | 15 | Collaboration | 2 | 2
|  |  | Planned Total | 365 | 100 | Actual Total | 105.5 | 207.5

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Design Team 9
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Mason Monday | 9,10,11 |  | 9,10,11 |  | 40 | 0 | 0 | 2 | 8 | 0 | 1 | 5 | 5 | 7 | 14
| Ansleigh Yancey |  |  |  |  | 50 | 4 | 5 | 2 | 4 | 0 | 1 | 4 | 12 | 10 | 22
| Paul Ryu | 9,10,11 | N/A | 9,10,11 | 9,10,11 | 30 | 0 | 0 | 3 | 11 | 1 | 1 | 4 | 5 | 8 | 17
| Sadaira Packer | 2011-09-10 |  |  | 9,10,11 | 40 | 0 | 0 | 9.5 | 17.5 | 0 | 0 | 2 | 2 | 11.5 | 19.5
| Ben Williams |  | 2019-09-11 |  |  | 30 | 0 | 0 | 1 | 3 | 0 | 1 | 6 | 10 | 7 | 14
[5 empty] | Totals | 190 | 4 | 5 | 17.5 | 43.5 | 1 | 4 | 21 | 34 | 43.5 | 86.5
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| We sat down for our weekly meeting and brainstormed how to merge the datasets together. We thought of a simple implementation but must test it to see whether or not it is efficient. | [6 empty] | Meet with the client and see if our idea is correct to him and if it is what he wants as the output.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| Group could not meet for an entire week. Some members were gone for long periods of time due to job interviews and the group in general had several scheduling conflicts that made meetings impossible. | [6 empty] | N/A
Risks facing the project:
Time to next cycle and the end of the project deadline is rapidly approaching. We must get a definite answer by the client in the next meeting in order to make significant progressions in the future.

## Mason Monday Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Mason Monday
Week Ending: |  | 2019-02-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2019-02-11 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed: | Analysis of datasets; defining required search requirements
Date: | 2019-02-12 | Result: | Better understanding of search requirements
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-13 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed: | Testing of front-end interface design
Date: | 2019-02-14 | Result: | Found small problems with searching function
Hours Worked: | 2 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-02-15 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-16 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-02-17 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-02-18 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed: | Testing of newest front-end version; analysis of datasets
Date: | 2019-02-19 | Result: | Small bugs found; comparison with small selection of each dataset provided a specific example we believe we can base the project off of
Hours Worked: | 3 | Problems encountered: | While we have been pairing this data mentally, we have not found a way to fully compare this data electroically
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-20 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-21 | Result:
Hours Worked: | ? | Problems encountered:

## Benjamin Williams Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Benjamin Williams
Week Ending: |  | 2019-02-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2019-02-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-02-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-02-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-02-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Worked on implementing search functionality based on chromosome start/end point.
Date: | 2019-02-20 | Result: | Many different attempts, could not filter the dataset. Using the wrong method would result in R crashing since the dataset is so big.
Hours Worked: | 3 | Problems encountered: | Could not access specific variables in the main dataset. Tried many different methods including subset, filter, indexing, creating a function, using the dataframe directly, etc. Also could not attend group meeting this night.
Day: | Thursday | Task(s) performed: | Continued working on intersecting the datasets to filter relevant information based on chromosome coordinates.
Date: | 2019-02-21 | Result: | Managed to filter dataset slightly (in progress past 3:00). Hope to be able to filter based on a user selecting a specific entry, and only showing entries that fall within the start/end point.
Hours Worked: | 4 | Problems encountered: | Working past 3:00 when status report is due. Still slightly unclear on what the correct implementation should look like; need to discuss with sponsor.

## Paul Ryu Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Paul Ryu
Week Ending: |  | 2019-02-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2019-02-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-12 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-13 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-14 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-02-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed: | Ran code written by Ben and looked for ways to search through the database using certain keywords.
Date: | 2019-02-17 | Result: | Figured out which parts of the dataset were not relevant to our project.
Hours Worked: | 1 | Problems encountered: | I thought that I found a pattern but it turned out to be unrelated. Haven't found a way to see which 'signals' are important yet.
Day: | Monday | Task(s) performed:
Date: | 2019-02-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Met with the team and brainstormed. I suggested an implementation that might be easily achievable through RStudio and R in general, but we still need to talk to the client to see if I am going in the right direction at all. I relayed the question to Mason so that he can ask the client during the next meeting.
Date: | 2019-02-20 | Result: | Created an implementation idea that MAY work.
Hours Worked: | 4 | Problems encountered: | We still do not have definite answer from the client on what he wants. Our only instruction right now is to "overlap the datasets together and create outputs".
Day: | Thursday | Task(s) performed: | Worked on this status report and kept playing around with the Integrative Genomics Viewer. I seem to be able to look up certain signals with chromosome coordinates, but sometimes they are empty when they should not be so I am trying to figure that issue out.
Date: | 2019-02-21 | Result: | Completed status report, better grasp of DNA/Nucleic Acid coordinates.
Hours Worked: | 3 | Problems encountered: | IGV is a very slow and old technology. It is also buggy and can crash unexpectedly if the JVM cannot handle it.

## Ansleigh Yancey Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Ansleigh Yancey
Week Ending: |  | 2019-02-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2019-02-11 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Worked more on the download portion of the user search tab. Tried to get .txt downloads implemented correctly
Date: | 2019-02-12 | Result: | Still some work to be done, but .txt files are downloadable for results
Hours Worked: | 2 | Problems encountered: | Issues with syntax still arise because I am still fairly new to the R and Shiny language and environment
Day: | Wednesday | Task(s) performed: | Experimented with different types of look and feel for the user interface. There are different page organizations and I want to explore all possibilities and find what looks best for our needs.
Date: | 2019-02-13 | Result: | Really like tabset and fluidpage layouts and am working at understanding other layouts as well
Hours Worked: | 3 | Problems encountered: | None
Day: | Thursday | Task(s) performed:
Date: | 2019-02-14 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed:
Date: | 2019-02-15 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-16 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-02-17 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Worked on email system for submission and deletion request system more.
Date: | 2019-02-18 | Result: | somewhat functioning, but still is in progress
Hours Worked: | 4 | Problems encountered: | a difficult task,but I will complete it
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-19 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Met with team mates and looked at current database. Brainstormed ways to classify diseases and made a new date to meet with our sponsor.
Date: | 2019-02-20 | Result: | contacted sponsor and researched data further
Hours Worked: | 1 | Problems encountered: | none
Day: | Thursday | Task(s) performed:
Date: | 2019-02-21 | Result:
Hours Worked: | ? | Problems encountered:

## Sadaira Packer Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Sadaira Packer
Week Ending: |  | 2019-02-21
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Monday | Task(s) performed:
Date: | 2019-02-11 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed: | Searched for links between the datasets.
Date: | 2019-02-12 | Result: | Better understanding of what a cell line is.
Hours Worked: | 2 | Problems encountered:
Day: | Wednesday | Task(s) performed: | Looked closer at the disease database. Examined the columns with clickable links to find more information that could possibly link the two datasets.
Date: | 2019-02-13 | Result:
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-14 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Friday | Task(s) performed: | Searched for academic papers on cell lines and diseases.
Date: | 2019-02-15 | Result: | Found a paper that discusses the architecture of a cell line database.
Hours Worked: | 1.5 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-16 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed: | Searched for information on how to know what disease coincides with a particular cell line. Looked over the code we have so far.
Date: | 2019-02-17 | Result: | I only came across other cell line databases that mentioned the related disease. Still unsure how they are connected.
Hours Worked: | 3 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-02-18 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-19 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Met with team. Looked at other cell line databases online. Individually searched a few cell lines from our database to see if it would lead to some sort of revelation.
Date: | 2019-02-20 | Result: | When searching the individual cell lines, I was able to see which disease they coincided with.
Hours Worked: | 3 | Problems encountered: | It would be impossible to do this for all 4 million entries.
Day: | Thursday | Task(s) performed:
Date: | 2019-02-21 | Result:
Hours Worked: | ? | Problems encountered: