## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Online Bio-Informatics Toolkit | [6 empty] | Completed | 1
| Team Members: | Paul Ryu, Ansleigh Yancey, Ben Williams, Mason Monday, Sadaira Packer | [6 empty] | Discarded | 2
| Date: | 2019-02-10 | Cycle: | 1 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To develop an interactive, online database that is searchable by disease type or tissue and cell lines. Users will also be able to request to add an entry into the database. | [6 empty] | In Review
Unstarted
| Cycle Intent: | To add functionality to search through a subset of our database based on cell line and/or disease type
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Add Entry Request(Text Box) |  | 2 | 30 | 0 | Collaboration | 6.5 | 6.5
2 | Add Entry Request(Text File) |  | 2 | 30 | 0 | Unstarted | 4 | 4
3 | Add Entry via Text Box(Administrator) |  | 2 | 20 | 5 | Unstarted | 0 | 0
4 | Add Entry via File(Administrator) |  | 2 | 20 | 0 | Unstarted | 0 | 0
5 | Delete Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
6 | Delete Entry(Administrator) |  | 2 | 20 | 0 | Unstarted | 0 | 0
7 | Edit Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
8 | Edit Entry(Administrator) |  | 2 | 25 | 0 | Unstarted | 0 | 0
9 | Search for Database Entry (Cell Line) |  | 1 | 40 | 20 | Collaboration | 47 | 47
10 | Search for Database Entry (Disease Type) |  | 1 | 40 | 20 | Collaboration | 47 | 47
11 | Search for Database Entry (Cell Line & Disease Type) |  | 1 | 40 | 40 | Collaboration | 44.5 | 44.5
12 | Download Search Results |  | 2 | 40 | 15 | Collaboration | 2 | 2
|  |  | Planned Total | 365 | 100 | Actual Total | 151 | 151

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Design Team 9
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Mason Monday | 9,10,11 |  | 9,10,11 |  | 40 | 0 | 0 | 2 | 10 | 0 | 1 | 6 | 11 | 8 | 22
| Ansleigh Yancey | 9,10,11 | 9,10,11 | 9,10,11 |  | 50 | 0 | 5 | 2 | 6 | 0 | 1 | 8 | 20 | 10 | 32
| Paul Ryu | 9,10,11 | 11 | N/A | 9,10,11 | 30 | 1 | 1 | 2 | 13 | 0 | 1 | 5 | 10 | 8 | 25
| Sadaira Packer | 9,10,11 | 9,10 |  | 9,10,11 | 40 | 0 | 0 | 2 | 19.5 | 0 | 0 | 6 | 8 | 8 | 27.5
| Ben Williams | 9,10,11 | 11 | N/A | 9,10,11 | 30 | 0 | 0 | 2 | 5 | 0 | 1 | 5 | 15 | 7 | 21
[5 empty] | Totals | 190 | 1 | 6 | 10 | 53.5 | 0 | 4 | 30 | 64 | 41 | 127.5
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| Since the last status report, we have researched individually, as suggested by Dr. Qin, the meanings and implications of the genome signals. We have looked into the correlations between those and disease types and shared what we discovered with each other. Further, we have made progress on the search functionality by implementing temporary search algorithms for the user inputs. We also edited our previous spike report in preparation for the upcoming spike report deliverable. | [6 empty] | When the client comes back into town, we will ask him whether or not our current plan aligns with what he wants. Specifically, we are going to find out whether or not looking up the Human (HG19) genomic signal cells with indices given in the disease / mutation phenotypes are correct. If so, we can create further plans to combine the datasets this way.
| Obstacles encountered since last status report: | [6 empty] | Notes:
| We attempted to find time to meet with our sponsor in regards to the specifics of database-prevalent data. However, we learned earlier this week that he would be out of town until the middle of next week. As we are currently at a standstill on the back-end portion of the project without his input, we decided to focus a bit more on the front-end side. Unfortunately for us, 95% of this project is pure backend procedures and it is the part that we are not getting any guidance on. We believe heavier pushing to get our sponsor to meet is necessary going forward. | [6 empty] | N/A
Risks facing the project:
The primary risk facing the project right now is lack of guidance from our sponsor. Understanding what parts of the data are useful and how to implement search functionality around intersecting two datasets is proving much more difficult than anticipated. Our sponsor is often out of town, and when he's in town, we have not found a time that every group member can meet with him at once.

## Mason Monday Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Mason Monday
Week Ending: |  | 2019-02-28
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-02-22 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed: | Testing functionality of Asleigh's front-end design
Date: | 2019-02-23 | Result: | Bug notes and fix ideas documented; will present to team next meeting
Hours Worked: | 3 | Problems encountered:
Day: | Sunday | Task(s) performed: | Testing functionality of Ben's front-end design
Date: | 2019-02-24 | Result: | Bug notes and fix ideas documented; discussed with Ben about future collaboratio with Ansleigh's design
Hours Worked: | 3 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-02-25 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-02-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed: | Data analysis on .bed file, hand-written detailing of proposed search algorithm
Date: | 2019-02-28 | Result: | Current theorhetical model for searching; will show to team and sponsor in our next meetings
Hours Worked: | 4 | Problems encountered: | Lack of information fro sposor makes process theorhetical, at best

## Benjamin Williams Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Benjamin Williams
Week Ending: |  | 2019-02-28
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-02-22 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-23 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed: | Discussed with Mason about the interaction between the Admin tab and the user tab
Date: | 2019-02-24 | Result: | Considering copying the same "X entries per page" functionality to the user tab.
Hours Worked: | 1 | Problems encountered: | Still somewhat unsure without guidance from sponsor.
Day: | Monday | Task(s) performed:
Date: | 2019-02-25 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-02-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Tried finding intersections in the datasets (i.e. cell tissues that relate to specific diseases)
Date: | 2019-02-27 | Result: | Still no luck.
Hours Worked: | 1 | Problems encountered: | Need sponsor's guidance.
Day: | Thursday | Task(s) performed: | Copied the "X entries per page" functionality to the user tab. Continued attempting to intersect the datasets by clicking on an entry and displaying all entries that fall within the range of the starting and stopping nucleotide numbers.
Date: | 2019-02-28 | Result: | "X entries per page" copied over. Currently working on search functionality by clicking entries.
Hours Worked: | 5 | Problems encountered: | The backend is still at a standstill so the changes I make are somewhat of a shot in the dark. Admin tab and user tabs were implemented differently, so my skills don't necessarily translate. Also, working past 3:00.

## Ansleigh Yancey Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Bio-Informatics Toolkit
Member: |  | Ansleigh Yancey
Week Ending: |  | 2019-02-10
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Friday | Task(s) performed: | researched more on how to make subsets of lists in R for temporary use
Date: | 2019-02-22 | Result: | gained understanding of how to implement search techniques
Hours Worked: | 1 | Problems encountered: | Still not completely clear on the criteria by which the actual search results should be found.
Day: | Saturday | Task(s) performed:
Date: | 2019-02-23 | Result:
Hours Worked: |  | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on search functionality of application as suggested by Dr. Qin
Date: | 2019-02-24 | Result: | Drop box choices for cell line yeild different (temporary) results from the data frame
Hours Worked: | 1.5 | Problems encountered:
Day: | Monday | Task(s) performed: | Worked further on the search functionality as Dr. Qin had suggested
Date: | 2019-02-25 | Result: | Drop box choices for disease type yeilds different (temporary) results from the data frame
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Edited work from the previous spike report that Dr. Qin noted to change
Date: | 2019-02-26 | Result: | Put use case stories into table structure and edited front page to add team member names
Hours Worked: | 0.5 | Problems encountered: | none
Day: | Wednesday | Task(s) performed: | Worked to make two drop box option yeild results that coincide with the choices the user inputs
Date: | 2019-02-27 | Result: | Works for some choices but not all
Hours Worked: | 2 | Problems encountered: | Struggling to understand sub-dataframe work using multiple variable inputs
Day: | Thursday | Task(s) performed: | Worked on editing and finalizing the status report as well as correcting the issues with the previous status report
Date: | 2019-02-28 | Result: | completed and turned in assignment and reworked hourly logs to find the correct values
Hours Worked: | 1.5 | Problems encountered:

## Sadaira Packer Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Sadaira Packer
Week Ending: |  | 2019-02-28
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-02-22 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-02-23 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed: | Worked on figuring out what all the options would be for the cell line and disease search bars, because there are duplicates.
Date: | 2019-02-24 | Result: | I was able to come up with the options for the disease database (541 options).
Hours Worked: | 2.5 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-02-25 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed: | Worked on figuring out what the options would befor the cell ine search bar.
Date: | 2019-02-26 | Result: | I have a rough estimate (101,514 entries).
Hours Worked: | 3.5 | Problems encountered: | This proved to be more difficult. The above number isn't necessarily correct because some of the entries have multiple cell lines separated by commas. I'm unsure how to get a true count of this.
Day: | Wednesday | Task(s) performed: | Worked on how to display the proper entries when the option is selected from the drop down menus.
Date: | 2019-02-27 | Result: | I need to figure out some sort of function to populate the options for the selectInput() function with the unique "Trait" variables
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-02-28 | Result:
Hours Worked: | ? | Problems encountered:

## Paul Ryu Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Paul Ryu
Week Ending: |  | 2019-02-28
Cycle: |  | Cycle 1
Team Member Work Summary
Day: | Friday | Task(s) performed: | Looked at method discussed last week and wrote basic search code to see if I could find a specific genome with an index.
Date: | 2019-02-22 | Result: | Some genomes were returned via entering an index.
Hours Worked: | 1 | Problems encountered: | Some genomes returned empty or null results.
Day: | Saturday | Task(s) performed: | N/A
Date: | 2019-02-23 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Sunday | Task(s) performed: | N/A
Date: | 2019-02-24 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Monday | Task(s) performed: | Looked further at the DNA indices to see if I could find the index points given by a specific mutation like Parkinson's in the human (HG19) data given to us by the client. Most were a match, and Googling them seemed to bring up results of signals that could possibly be correlated to a disease.
Date: | 2019-02-25 | Result: | Matched some mutation data to genome signals successfully.
Hours Worked: | 4 | Problems encountered: | At some index points, there was nothing there in the human DNA. I am not sure if it's because the genetic mutation has nothing to do with that particular signal.
Day: | Tuesday | Task(s) performed: | N/A
Date: | 2019-02-26 | Result: | N/A
Hours Worked: | 0 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed: | Spoke with Mason about my progress and data collected and he contacted the client to see if our methodology was correct.
Date: | 2019-02-27 | Result: | Relayed more backend information and issues to teammate.
Hours Worked: | 2 | Problems encountered: | Client responded, saying that he is out of town until next week. This is a persistent problem and we are doing our best to press him for more help. Without his guidance on the very complex parts of the data, we are not able to write any code for the backend even as five people because we do not understand what data must be manipulated.
Day: | Thursday | Task(s) performed: | Worked on the Status Report and communicated with the team what our issues are and what we need to do when the client comes back.
Date: | 2019-02-28 | Result: | Established communications with team and made plans.
Hours Worked: | 1 | Problems encountered: | None