## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Online Bio-Informatics Toolkit | [6 empty] | Completed | 1
| Team Members: | Paul Ryu, Ansleigh Yancey, Ben Williams, Mason Monday, Sadaira Packer | [6 empty] | Discarded | 2
| Date: | 2019-03-22 | Cycle: | 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To develop an interactive, online database that is searchable by disease type or tissue and cell lines. Users will also be able to request to add an entry into the database. | [6 empty] | In Review
Unstarted
| Cycle Intent: | To complete the search functionality such that the output merges both datasets, and create the option to dynamically replace one of the datasets via text box or text file.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Add Entry Request(Text Box) |  | 2 | 30 | 30 | Collaboration |  | 6.5
2 | Add Entry Request(Text File) |  | 2 | 30 | 30 | Collaboration |  | 4
3 | Add Entry via Text Box(Administrator) |  | 2 | 20 | 30 | Collaboration |  | 0
4 | Add Entry via File(Administrator) |  | 2 | 20 | 30 | Collaboration |  | 0
5 | Delete Entry Request |  | 3 | 30 | 0 | Unstarted |  | 0
6 | Delete Entry(Administrator) |  | 2 | 20 | 20 | Collaboration |  | 0
7 | Edit Entry Request |  | 3 | 30 | 0 | Unstarted |  | 0
8 | Edit Entry(Administrator) |  | 2 | 25 | 25 | Unstarted |  | 0
9 | Search for Database Entry (Cell Line) |  | 1 | 40 | 5 | In Review |  | 47
10 | Search for Database Entry (Disease Type) |  | 1 | 40 | 5 | In Review |  | 47
11 | Search for Database Entry (Cell Line & Disease Type) |  | 1 | 40 | 10 | In Review | 3 | 44.5
12 | Download Search Results |  | 2 | 40 | 40 | Collaboration |  | 2
|  |  | Planned Total | 365 | 225 | Actual Total | 3 | 151

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Design Team 9
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Mason Monday |  |  | 9,10 |  | 40 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4
| Ansleigh Yancey |  |  |  |  | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Paul Ryu |  |  | 9,10,11 |  | 40 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 4 | 4
| Sadaira Packer |  | 9,10,11 | 9,10,11 |  | 40 | 0 | 0 | 4.5 | 4.5 | 0 | 0 | 0 | 0 | 4.5 | 4.5
| Ben Williams |  | 11 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3
[5 empty] | Totals | 210 | 0 | 0 | 12.5 | 12.5 | 0 | 0 | 3 | 3 | 15.5 | 15.5
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| We were able to get more information from the client and are now able to focus on the higher level aspects of organizing/sorting the datasets. | [6 empty] | After figuring out how to organize the higher-level parts of the datasets efficiently and accurately, like medical categories, the objective is to observe the pieces of data that the client has specified to be used and figure out ways to do lower level merging of datasets, such as using index points for chromosomes and pairing them with genomic cell line counterparts.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Paul: I was absent for several meetings due to many job interviews and my teammates had to pick up my slack from those days.
Risks facing the project:
We fell a little behind while our sponsor was unavailable and have a little bit of catching up to do.

## Sadaira Packer Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Sadaira Packer
Week Ending: |  | 2019-03-22
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-16 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-17 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Reviewed the information from both datasets that is needed to connect them.
Date: | 2019-03-18 | Result: | Focused mainly on chromosome columns in the cell line dataset and the position, trait, mesh trait columns in the trait dataset.
Hours Worked: | 1.5 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-19 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Looked into how to retrieve the proper outputs for the traits & mesh traits input.
Date: | 2019-03-20 | Result: | When a trait is selected, the position is used and matched whith the cell line data entries that have that position in their chromosome range.
Hours Worked: | 3 | Problems encountered: | The cell line database has a large amount of entries. I haven't figured out how to do this efficiently yet.
Day: | Thursday | Task(s) performed:
Date: | 2019-03-21 | Result:
Hours Worked: | ? | Problems encountered:

## Paul Ryu Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Paul Ryu
Week Ending: |  | 2019-03-22
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Communicated with Ansleigh about how her UI was doing and reviewed the new data that the client (Dr. Chen) specified for us to use.
Date: | 2019-03-19 | Result: | Directed focus to specific datasets, specifically Medical Categories and Diseases.
Hours Worked: | 2 | Problems encountered: | N/A
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Worked on the Status Report. Researched how to take on the next big obstacle of the project, which is to delve further into the datasets and compare/sort on a chromosome level.
Date: | 2019-03-21 | Result: | Understand more of what the long/short arms of chromosomes mean and how to use their focal points to organize chromosome data by indices.
Hours Worked: | 2 | Problems encountered: | N/A

## Mason Monday Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Mason Monday
Week Ending: |  | 2019-03-22
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-16 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-17 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Testing on current search functionality(User Story #9)
Date: | 2019-03-18 | Result: | No faults found
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-19 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Testing on current search functionality(User Story #10)
Date: | 2019-03-20 | Result: | No faults found
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-21 | Result:
Hours Worked: | ? | Problems encountered:

## Benjamin Williams Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Benjamin Williams
Week Ending: |  | 2019-03-22
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-16 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-17 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-18 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-19 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-20 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Worked on merging the relevant information in each dataset into one table as output when a trait is selected
Date: | 2019-03-21 | Result: | Output should be in the correct format - 13 columns consisting of data from both datasets
Hours Worked: | 3 | Problems encountered: | N/A since work will be done past 3:00

## Ansleigh Yancey Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Ansleigh Yancey
Week Ending: |  | 2019-03-22
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-15 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-16 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-17 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-18 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-19 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-20 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-21 | Result:
Hours Worked: | ? | Problems encountered: