## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Online Bio-Informatics Toolkit | [6 empty] | Completed | 1
| Team Members: | Paul Ryu, Ansleigh Yancey, Ben Williams, Mason Monday, Sadaira Packer | [6 empty] | Discarded | 2
| Date: | 2019-03-29 | Cycle: | 2 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To develop an interactive, online database that is searchable by disease type or tissue and cell lines. Users will also be able to request to add an entry into the database. | [6 empty] | In Review
Unstarted
| Cycle Intent: | To complete the search functionality such that the output merges both datasets, and create the option to dynamically replace one of the datasets via text box or text file.
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Add Entry Request(Text Box) |  | 3 | 30 | 5 | Collaboration |  | 6.5
2 | Add Entry Request(Text File) |  | 3 | 30 | 5 | Collaboration |  | 4
3 | Add Entry via Text Box(Administrator) |  | 3 | 20 | 5 | Collaboration |  | 0
4 | Add Entry via File(Administrator) |  | 3 | 20 | 5 | Collaboration |  | 0
5 | Delete Entry Request |  | 3 | 30 | 5 | Unstarted |  | 0
6 | Delete Entry(Administrator) |  | 3 | 20 | 5 | Collaboration |  | 0
7 | Edit Entry Request |  | 3 | 30 | 5 | Unstarted |  | 0
8 | Edit Entry(Administrator) |  | 2 | 25 | 5 | Unstarted |  | 0
9 | Search for Database Entry (Cell Line) |  | 2 | 40 | 15 | In Review | 12.5 | 59.5
10 | Search for Database Entry (Disease Type) |  | 2 | 40 | 15 | In Review | 16.5 | 63.5
11 | Search for Database Entry (Cell Line & Disease Type) |  | 2 | 40 | 15 | In Review | 22.5 | 66.5
12 | Download Search Results |  | 3 | 40 | 5 | Collaboration |  | 2
|  |  | Planned Total | 365 | 90 | Actual Total | 51.5 | 202

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Design Team 9
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Mason Monday | 1,2,3,4 |  | 9,10 |  | 40 | 0 | 0 | 2 | 6 | 0 | 0 | 2 | 2 | 4 | 8
| Ansleigh Yancey | 9,10,11 | 9,10,11 |  |  | 50 | 0 | 0 | 3 | 3 | 0 | 0 | 5 | 14 | 8 | 17
| Paul Ryu |  |  | 9,10,11 |  | 40 | 0 | 0 | 3 | 6 | 0 | 0 | 3 | 3 | 6 | 9
| Sadaira Packer |  | 9,10 | 9,10,11 |  | 40 | 0 | 0 |  | 4.5 | 0 | 0 | 8 | 8 | 8 | 12.5
| Ben Williams |  | 11 |  |  | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 8 | 5 | 8
[5 empty] | Totals | 210 | 0 | 0 | 8 | 19.5 | 0 | 0 | 23 | 35 | 31 | 54.5
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| We were able to get more information from the client and are now able to focus on the higher level aspects of organizing/sorting the datasets. | [6 empty] | Prioritize writing more source code to back the new information that the client gave us for the back-end. Once that is finished, we can link it to the front-end or UI.
| Obstacles encountered since last status report: | [6 empty] | Notes:
Risks facing the project:
The only real risk is running out of time to finish, which we expect will not be an issue.

## Sadaira Packer Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Sadaira Packer
Week Ending: |  | 2019-03-29
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-22 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-23 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-24 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Worked on searching by trait
Date: | 2019-03-25 | Result: | I'm able to click on a trait and have all of the proper results from the trait dataset come up.
Hours Worked: | 3 | Problems encountered: | I'm not sure how to get the proper cell lines correspond to the position of the traits.
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Worked on displaying the cell line table
Date: | 2019-03-27 | Result: | I think I know logically how to do it, just haven't fully executed it.
Hours Worked: | 3.5 | Problems encountered:
Day: | Thursday | Task(s) performed: | Worked on searching by Mesh category
Date: | 2019-03-28 | Result: | I'm able to click on a mesh category and have all of the proper results from the trait dataset come up.
Hours Worked: | 1.5 | Problems encountered: | I'm not sure how to get the proper cell lines correspond to the position of the traits.

## Paul Ryu Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Paul Ryu
Week Ending: |  | 2019-03-29
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-22 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-23 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-24 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-25 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Tuesday | Task(s) performed: | Worked on separating the data and making it more readable. Removed lines of disease/mutation data that are not necessary in the scope of this project.
Date: | 2019-03-26 | Result: | Mesh categories and their respective contexts are now much more easy to understand and sift through.
Hours Worked: | 3 | Problems encountered: | Finding new ways to coorelate the categories to the cell lines is still proving to be difficult.
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-27 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Moved on from organizing traits. Started working on separating the SNP and P-Values. Communicated with Mason to clarify with the team what the next steps are with the client's datasets.
Date: | 2019-03-28 | Result: | I can now move onto the more complicated portions of our data like SNP, gene regions, and chromosome positions.
Hours Worked: | 3 | Problems encountered: | Some of the necessary data, like P-Values, are numbers that were taught in freshman level Statistics courses and I do not remember any of it. I will have to look up how to calculate and organize P-values, which is now a bit out of scope for our project.

## Mason Monday Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Mason Monday
Week Ending: |  | 2019-03-29
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-22 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-23 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-24 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed: | Designing methods for User Stories 1-4
Date: | 2019-03-25 | Result: | Pseudocode representation for these user stories; will discuss with team during next meeting
Hours Worked: | 2 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | Testing on User Stories 9 and 10
Date: | 2019-03-27 | Result: | Fixed small bugs found in the current code; process working more smoothly
Hours Worked: | 2 | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-03-28 | Result:
Hours Worked: | ? | Problems encountered:

## Benjamin Williams Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Benjamin Williams
Week Ending: |  | 2019-03-29
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-22 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-03-23 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-03-24 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-03-25 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-03-27 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed: | Worked on displaying output as one table consisting of select columns from the primary database and dynamic disease dataset, where the data overlaps.
Date: | 2019-03-28 | Result: | Mega-table created and displayed.
Hours Worked: | 5 | Problems encountered: | Working past 3:00

## Ansleigh Yancey Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Ansleigh Yancey
Week Ending: |  | 2019-03-29
Cycle: |  | Cycle 2
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-03-22 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed: | worked on a new banner for the website
Date: | 2019-03-23 | Result: | came up with a few new options to choose from
Hours Worked: | 1.5 | Problems encountered:
Day: | Sunday | Task(s) performed: | researched how input box selection techniques and watched tutorials for the implementation for R in Shiny
Date: | 2019-03-24 | Result: | gained a better understanding of what needs to be done
Hours Worked: | 1.5 | Problems encountered:
Day: | Monday | Task(s) performed: | worked making the mesh trait drop down box options change with the corresponding trait drop down box selections
Date: | 2019-03-25 | Result: | made some progress, but there is much do be done
Hours Worked: | 3 | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-03-26 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed: | worked more on the drop down box implementation
Date: | 2019-03-27 | Result: | got one selection to work correctly but the rest do not
Hours Worked: | 2 | Problems encountered: | difficult to implement and understand, but doable in the end
Day: | Thursday | Task(s) performed:
Date: | 2019-03-28 | Result:
Hours Worked: | ? | Problems encountered: