## Status Report Page 1
Senior Design Status Report (Page 1) | [8 empty] | List Data - Do Not Edit
| Project Name: | Online Bio-Informatics Toolkit | [6 empty] | Completed | 1
| Team Members: | Paul Ryu, Ansleigh Yancey, Ben Williams, Mason Monday, Sadaira Packer | [6 empty] | Discarded | 2
| Date: | 2019-04-12 | Cycle: | 3 |  |  |  |  | Collaboration | 3
Adversarial
| System Metaphor: | To develop an interactive, online database that is searchable by disease type or tissue and cell lines. Users will also be able to request to add an entry into the database. | [6 empty] | In Review
Unstarted
| Cycle Intent: | TO BE ADDED
|  |  | Planned |  |  | Actual
# | User Story |  | Cycle planned for completion | Total planned hours | Planned hours this cycle | Status | Actual hours this cycle | Total hours
1 | Add Entry Request(Text Box) |  | 3 | 30 | 0 | Collaboration | 0 | 6.5
2 | Add Entry Request(Text File) |  | 3 | 30 | 0 | Collaboration | 0 | 4
3 | Add Entry via Text Box(Administrator) |  | 3 | 20 | 0 | Collaboration | 0 | 0
4 | Add Entry via File(Administrator) |  | 3 | 20 | 0 | Collaboration | 0 | 0
5 | Delete Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
6 | Delete Entry(Administrator) |  | 3 | 20 | 0 | Collaboration | 0 | 0
7 | Edit Entry Request |  | 3 | 30 | 0 | Unstarted | 0 | 0
8 | Edit Entry(Administrator) |  | 2 | 25 | 0 | Unstarted | 0 | 0
9 | Search for Database Entry (Cell Line) |  | 2 | 40 | 0 | In Review | 0 | 59.5
10 | Search for Database Entry (Disease Type) |  | 2 | 40 | 0 | In Review | 0 | 63.5
11 | Search for Database Entry (Cell Line & Disease Type) |  | 2 | 40 | 0 | In Review | 0 | 66.5
12 | Download Search Results |  | 3 | 40 | 0 | Collaboration | 0 | 2
|  |  | Planned Total | 365 | 0 | Actual Total | 0 | 202

## Page 2
Senior Design Status Report (Page 2)
| Team Name: | Design Team 9
|  | User Stories |  |  |  | Planned | Actual
| Member Name | Collab | Code | Test | Review | Planned hours this cycle | Refactor Hours |  | Process Hours |  | Customer Hours |  | Product Hours |  | Total Hours
[7 empty] | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle | Week | Cycle
| Mason Monday |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ansleigh Yancey |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Paul Ryu |  |  |  |  | 40 | 2 | 2 | 3 | 3 | 0 | 0 | 4 | 4 | 0 | 9
| Sadaira Packer |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ben Williams |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Totals | 40 | 2 | 2 | 3 | 3 | 0 | 0 | 4 | 4 | 0 | 9
| Accomplishments since last status report: | [6 empty] | Objectives for the next week:
| TO BE ADDED | [6 empty] | TO BE ADDED
| Obstacles encountered since last status report: | [6 empty] | Notes:
| TO BE ADDED | [6 empty] | TO BE ADDED
Risks facing the project:
TO BE ADDED

## Sadaira Packer Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Sadaira Packer
Week Ending: |  | 2019-04-12
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-04-05 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-06 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-08 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-04-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-04-10 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-04-11 | Result:
Hours Worked: | ? | Problems encountered:

## Paul Ryu Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Paul Ryu
Week Ending: |  | 2019-04-12
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-04-05 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-06 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Monday | Task(s) performed: | Communicated with the team about what needs to be done next. We came up with a plan to remove an unnecessary functionality in our web application and looked into new ways to organize the large amount of data.
Date: | 2019-04-08 | Result: | Came up with a roadmap with the team for the remainder of the project.
Hours Worked: | 3 | Problems encountered: | We found that the team lacks database experience.
Day: | Tuesday | Task(s) performed: | Obtained/read books on SQL and researched dplyr/DBI packages (Shiny's packages for databases). I also took into account what Dr. Qin and Austin Osborn suggested after our presentation, which was to look into database indexing. I also researched that issue and also how to prevent SQL injections with R Shiny to address one of our mitigation risks.
Date: | 2019-04-09 | Result: | Learned a lot about SQL, general database techniques, and indexing.
Hours Worked: | 3 | Problems encountered: | Not sure how to use indexing correctly with our datasets yet.
Day: | Wednesday | Task(s) performed:
Date: | 2019-04-10 | Result:
Hours Worked: | 0 | Problems encountered:
Day: | Thursday | Task(s) performed: | Worked on the Status Report. Refactored and created documentation for our source code so far.
Date: | 2019-04-11 | Result: | Code is more readable and understandable.
Hours Worked: | 3 | Problems encountered:

## Mason Monday Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Mason Monday
Week Ending: |  | 2019-04-12
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-04-05 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-06 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-08 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-04-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-04-10 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-04-11 | Result:
Hours Worked: | ? | Problems encountered:

## Benjamin Williams Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Benjamin Williams
Week Ending: |  | 2019-04-12
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-04-05 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-06 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-08 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-04-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-04-10 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-04-11 | Result:
Hours Worked: | ? | Problems encountered:

## Ansleigh Yancey Timesheet
COMP4710 Status Report - Member Timesheet
Project Name: |  | Online Bio-Informatics Toolkit
Member: |  | Ansleigh Yancey
Week Ending: |  | 2019-04-12
Cycle: |  | Cycle 3
Team Member Work Summary
Day: | Friday | Task(s) performed:
Date: | 2019-04-05 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Saturday | Task(s) performed:
Date: | 2019-04-06 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Sunday | Task(s) performed:
Date: | 2019-04-07 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Monday | Task(s) performed:
Date: | 2019-04-08 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Tuesday | Task(s) performed:
Date: | 2019-04-09 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Wednesday | Task(s) performed:
Date: | 2019-04-10 | Result:
Hours Worked: | ? | Problems encountered:
Day: | Thursday | Task(s) performed:
Date: | 2019-04-11 | Result:
Hours Worked: | ? | Problems encountered: